## Activities
CONTRACT TIME CALCULATION
Preliminary Estimate
Project ID |  |  | UPN/Unit |  |  | Designer
Description |  |  | Length |  | mi. | Date | 2025-03-04
Type
Activity No. | Work Activity |  |  | Production |  | Duration |  | Preceding Activities
| Item | Quantity | Unit | Rate | Unit | Work | Other
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
Key Dates:
Comments:
Page 1
CONTRACT TIME CALCULATION
Preliminary Estimate
Project ID | 0 |  | UPN/Unit | 0 |  | Designer | 0
Description | 0 |  | Length | 0 | mi. | Date | 2025-03-04
Type | 0
Activity No. | Work Activity |  |  | Production |  | Duration |  | Preceding Activities
| Item | Quantity | Unit | Rate | Unit | Work | Other
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
Key Dates:
Comments:
Page 2
CONTRACT TIME CALCULATION
Preliminary Estimate
Project ID | 0 |  | UPN/Unit | 0 |  | Designer | 0
Description | 0 |  | Length | 0 | mi. | Date | 2025-03-04
Type | 0
Activity No. | Work Activity |  |  | Production |  | Duration |  | Preceding Activities
| Item | Quantity | Unit | Rate | Unit | Work | Other
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
Key Dates:
Comments:
Page 3
CONTRACT TIME CALCULATION
Preliminary Estimate
Project ID | 0 |  | UPN/Unit | 0 |  | Designer | 0
Description | 0 |  | Length | 0 | mi. | Date | 2025-03-04
Type | 0
Activity No. | Work Activity |  |  | Production |  | Duration |  | Preceding Activities
| Item | Quantity | Unit | Rate | Unit | Work | Other
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
Key Dates:
Comments:
Page 4
Note on K2: Harris, Brett S: The Project ID, Description, etc. can be iput into Page 1. The following pages will autopopulate.

## Schedule
CONTRACT TIME CALCULATION
Preliminary Estimate
Project ID | [57 empty] | UPN/Unit | [34 empty] | Designer
Description | [57 empty] | Length | [21 empty] | mi. | [12 empty] | Date | [10 empty] | 2025-03-04
Type
[133 empty] | NTP Start Day | 0
Act. No. | Pre.Act. | Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130
|  |  | 1: 1; 2: 2; 4: 5; 9: 10; 14: 15; 19: 20; 29: 30; 39: 40; 49: 50; 59: 60; 69: 70; 79: 80; 89: 90; 98: 100; 108: 110; 118: 120; 127: 130 | Activity Begin | Activity End | Act. No. | Pre. Act. | Day | Activity Begin | Activity End
1 |  |  | 1: 0 | 0 |  | 1 |  |  | 0 | #VALUE!
2 |  |  | 1: 0 |  |  | 2 |  |  | #N/A | #N/A
3 |  |  | 1: 0 |  |  | 3 |  |  | #N/A | #N/A
4 |  |  | 1: 0 |  |  | 4 |  |  | #N/A | #N/A
5 |  |  | 1: 0 |  |  | 5 |  |  | #N/A | #N/A
6 |  |  | 1: 0 |  |  | 6 |  |  | #N/A | #N/A
7 |  |  | 1: 0 |  |  | 7 |  |  | #N/A | #N/A
8 |  |  | 1: 0 |  |  | 8 |  |  | #N/A | #N/A
9 |  |  | 1: 0 |  |  | 9 |  |  | #N/A | #N/A
10 |  |  | 1: 0 |  |  | 10 |  |  | #N/A | #N/A
11 |  |  | 1: 0 |  |  | 11 |  |  | #N/A | #N/A
12 |  |  | 1: 0 |  |  | 12 |  |  | #N/A | #N/A
13 |  |  | 1: 0 |  |  | 13 |  |  | #N/A | #N/A
14 |  |  | 1: 0 |  |  | 14 |  |  | #N/A | #N/A
15 |  |  | 1: 0 |  |  | 15 |  |  | #N/A | #N/A
16 |  |  | 1: 0 |  |  | 16 |  |  | #N/A | #N/A
17 |  |  | 1: 0 |  |  | 17 |  |  | #N/A | #N/A
18 |  |  | 1: 0 |  |  | 18 |  |  | #N/A | #N/A
19 |  |  | 1: 0 |  |  | 19 |  |  | #N/A | #N/A
20 |  |  | 1: 0 |  |  | 20 |  |  | #N/A | #N/A
21 |  |  | 1: 0 |  |  | 21 |  |  | #N/A | #N/A
22 |  |  | 1: 0 |  |  | 22 |  |  | #N/A | #N/A
23 |  |  | 1: 0 |  |  | 23 |  |  | #N/A | #N/A
24 |  |  | 1: 0 |  |  | 24 |  |  | #N/A | #N/A
25 |  |  | 1: 0 |  |  | 25 |  |  | #N/A | #N/A
26 |  |  | 1: 0 |  |  | 26 |  |  | #N/A | #N/A
[135 empty] | 27 |  |  | #N/A | #N/A
[135 empty] | 28 |  |  | #N/A | #N/A
|  |  | 1: Working Days:; 21: * 1.1 =; 31: 0 |  |  | 29 |  |  | #N/A | #N/A
|  |  | 21: Use; 31: 0 |  |  | 30 |  |  | #N/A | #N/A
[135 empty] | 31 |  |  | #N/A | #N/A
[135 empty] | 32 |  |  | #N/A | #N/A
[135 empty] | 33 |  |  | #N/A | #N/A
|  |  | 121: Page 1 |  |  | 34 |  |  | #N/A | #N/A
CONTRACT TIME CALCULATION | [134 empty] | 35 |  |  | #N/A | #N/A
Preliminary Estimate | [134 empty] | 36 |  |  | #N/A | #N/A
[135 empty] | 37 |  |  | #N/A | #N/A
Project ID |  |  | 56: UPN/Unit; 91: Designer |  |  | 38 |  |  | #N/A | #N/A
Description |  |  | 56: Length; 78: mi.; 91: Date; 102: 2025-03-04 |  |  | 39 |  |  | #N/A | #N/A
Type | [134 empty] | 40 |  |  | #N/A | #N/A
[135 empty] | 41 |  |  | #N/A | #N/A
Act. No. | Pre.Act. | Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 |  |  | 42 |  |  | #N/A | #N/A
|  |  | 8: 10; 18: 20; 28: 30; 38: 40; 48: 50; 58: 60; 68: 70; 78: 80; 88: 90; 98: 100; 108: 110; 118: 120; 127: 130 | Activity Begin | Activity End | 43 |  |  | #N/A | #N/A | Activity Begin Offset
27 |  |  | 1: 0 |  |  | 44 |  |  | #N/A | #N/A | 0
28 |  |  | 1: 0 |  |  | 45 |  |  | #N/A | #N/A
29 |  |  | 1: 0 |  |  | 46 |  |  | #N/A | #N/A
30 |  |  | 1: 0 |  |  | 47 |  |  | #N/A | #N/A
31 |  |  | 1: 0 |  |  | 48 |  |  | #N/A | #N/A
32 |  |  | 1: 0 |  |  | 49 |  |  | #N/A | #N/A
33 |  |  | 1: 0 |  |  | 50 |  |  | #N/A | #N/A
34 |  |  | 1: 0 |  |  | 51 |  |  | #N/A | #N/A
35 |  |  | 1: 0 |  |  | 52 |  |  | #N/A | #N/A
36 |  |  | 1: 0 |  |  | 53 |  |  | #N/A | #N/A
37 |  |  | 1: 0 |  |  | 54 |  |  | #N/A | #N/A
38 |  |  | 1: 0 |  |  | 55 |  |  | #N/A | #N/A
39 |  |  | 1: 0 |  |  | 56 |  |  | #N/A | #N/A
40 |  |  | 1: 0 |  |  | 57 |  |  | #N/A | #N/A
41 |  |  | 1: 0 |  |  | 58 |  |  | #N/A | #N/A
42 |  |  | 1: 0 |  |  | 59 |  |  | #N/A | #N/A
43 |  |  | 1: 0 |  |  | 60 |  |  | #N/A | #N/A
44 |  |  | 1: 0 |  |  | 61 |  |  | #N/A | #N/A
45 |  |  | 1: 0 |  |  | 62 |  |  | #N/A | #N/A
46 |  |  | 1: 0 |  |  | 63 |  |  | #N/A | #N/A
47 |  |  | 1: 0 |  |  | 64 |  |  | #N/A | #N/A
48 |  |  | 1: 0 |  |  | 65 |  |  | #N/A | #N/A
49 |  |  | 1: 0 |  |  | 66 |  |  | #N/A | #N/A
50 |  |  | 1: 0 |  |  | 67 |  |  | #N/A | #N/A
51 |  |  | 1: 0 |  |  | 68 |  |  | #N/A | #N/A
52 |  |  | 1: 0 |  |  | 69 |  |  | #N/A | #N/A
[135 empty] | 70 |  |  | #N/A | #N/A
[135 empty] | 71 |  |  | #N/A | #N/A
|  |  | 1: Working Days:; 21: * 1.1 =; 31: 0 |  |  | 72 |  |  | #N/A | #N/A
|  |  | 21: Use; 31: 0 |  |  | 73 |  |  | #N/A | #N/A
[135 empty] | 74 |  |  | #N/A | #N/A
[135 empty] | 75 |  |  | #N/A | #N/A
[135 empty] | 76 |  |  | #N/A | #N/A
|  |  | 121: Page 2 |  |  | 77 |  |  | #N/A | #N/A
CONTRACT TIME CALCULATION | [134 empty] | 78 |  |  | #N/A | #N/A
Preliminary Estimate | [134 empty] | 79 |  |  | #N/A | #N/A
[135 empty] | 80 |  |  | #N/A | #N/A
Project ID |  |  | 56: UPN/Unit; 91: Designer |  |  | 81 |  |  | #N/A | #N/A
Description |  |  | 56: Length; 78: mi.; 91: Date; 102: 2025-03-04 |  |  | 82 |  |  | #N/A | #N/A
Type | [134 empty] | 83 |  |  | #N/A | #N/A
[135 empty] | 84 |  |  | #N/A | #N/A
Act. No. | Pre.Act. | Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 |  |  | 85 |  |  | #N/A | #N/A
|  |  | 8: 10; 18: 20; 28: 30; 38: 40; 48: 50; 58: 60; 68: 70; 78: 80; 88: 90; 98: 100; 108: 110; 118: 120; 127: 130 | Activity Begin | Activity End | 86 |  |  | #N/A | #N/A | Activity Begin Offset
53 |  |  | 1: 0 |  |  | 87 |  |  | #N/A | #N/A | 0
54 |  |  | 1: 0 |  |  | 88 |  |  | #N/A | #N/A
55 |  |  | 1: 0 |  |  | 89 |  |  | #N/A | #N/A
56 |  |  | 1: 0 |  |  | 90 |  |  | #N/A | #N/A
57 |  |  | 1: 0 |  |  | 91 |  |  | #N/A | #N/A
58 |  |  | 1: 0 |  |  | 92 |  |  | #N/A | #N/A
59 |  |  | 1: 0 |  |  | 93 |  |  | #N/A | #N/A
60 |  |  | 1: 0 |  |  | 94 |  |  | #N/A | #N/A
61 |  |  | 1: 0 |  |  | 95 |  |  | #N/A | #N/A
62 |  |  | 1: 0 |  |  | 96 |  |  | #N/A | #N/A
63 |  |  | 1: 0 |  |  | 97 |  |  | #N/A | #N/A
64 |  |  | 1: 0 |  |  | 98 |  |  | #N/A | #N/A
65 |  |  | 1: 0 |  |  | 99 |  |  | #N/A | #N/A
66 |  |  | 1: 0 |  |  | 100 |  |  | #N/A | #N/A
67 |  |  | 1: 0
68 |  |  | 1: 0
69 |  |  | 1: 0
70 |  |  | 1: 0
71 |  |  | 1: 0
72 |  |  | 1: 0
73 |  |  | 1: 0
74 |  |  | 1: 0
75 |  |  | 1: 0
76 |  |  | 1: 0
77 |  |  | 1: 0
78 |  |  | 1: 0
|  |  | Working Days: | [19 empty] | * 1.1 = | [9 empty] | 0
[23 empty] | Use | [9 empty] | 0
Page 3
CONTRACT TIME CALCULATION
Preliminary Estimate
Project ID |  |  | 56: UPN/Unit; 91: Designer
Description |  |  | 56: Length; 78: mi.; 91: Date; 102: 2025-03-04
Type
Act. No. | Pre.Act. | Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130
|  |  | 8: 10; 18: 20; 28: 30; 38: 40; 48: 50; 58: 60; 68: 70; 78: 80; 88: 90; 98: 100; 108: 110; 118: 120; 127: 130 | Activity Begin | Activity End | [5 empty] | Activity Begin Offset
79 |  |  | 1: 0 | [7 empty] | 0
80 |  |  | 1: 0
81 |  |  | 1: 0
82 |  |  | 1: 0
83 |  |  | 1: 0
84 |  |  | 1: 0
85 |  |  | 1: 0
86 |  |  | 1: 0
87 |  |  | 1: 0
88 |  |  | 1: 0
89 |  |  | 1: 0
90 |  |  | 1: 0
91 |  |  | 1: 0
92 |  |  | 1: 0
93 |  |  | 1: 0
94 |  |  | 1: 0
95 |  |  | 1: 0
96 |  |  | 1: 0
97 |  |  | 1: 0
98 |  |  | 1: 0
99 |  |  | 1: 0
100 |  |  | 1: 0
|  |  | Working Days: | [19 empty] | * 1.1 = | [9 empty] | 0
[23 empty] | Use | [9 empty] | 0
Page 4
Note on EE2: Harris, Brett S: All of the cells in this spreadsheet tab should auto-populate based on what is entered into the "Activities Tab". Editing cells in ths tab may result in broken equations and errors.
Note on EF7: Harris, Brett S: Do not edit information in Columns EF and EG. These are only necessary in order for equations to calculate correctly.
Note on EN13: Harris, Brett S: The color of the activities in the schedule can be changed by doing the following: 1) Click on the row which you would like to change. 2) Click on "Conditional Formatting" at the top middle of the screen. 3) Click on "Manage Rules". 4) Click on the rule, then select "Edit Rule". 5) Click "Format" in the window that appears. 6) Click on "Fill", then select the preferred color.
Note on AH38: Harris, Brett S: If the result is displaying "#VALUE", click in this cell to display the equation, and drag the range in column EG to include all "Activity End" values.
Note on EF52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These are non-editable cells. Only edit if you need more activities added beyond 27.
Note on EN52: Harris, Brett S: The offset boxes can be used to shift the schedule to the right by the amount of days entered. This may be needed if an activity on this page has a predecessor on page 1 which may pre-date Activity 27.
Note on EF95: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These are non-editable cells. Only edit if you need more activities added beyond 27.
Note on EF138: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These are non-editable cells. Only edit if you need more activities added beyond 27.

## Production Rates
Average Production Rates | [5 empty] | April 2008
|  |  | Metric Production |  | English Production
Work Activity |  | Type | Rate | Unit | Rate | Unit
Moblilization | Size method | Small (seal coat) | 2 | days min | 2 | days min
|  | Medium (< $2mil) | 5 | days | 5 | days
|  | Large (> $2mil) | 8 | days | 8 | days
|  | Extra Large (> $10mil) | 15 | days | 15 | days
BMP | Size method | Small (seal coat) | 2 | days | 2 | days
(or include in mob) |  | Medium (< $2mil) | 4 | days | 4 | days
|  | Large (> $2mil) | 6 | days | 6 | days
Earthwork | Topsoil | Small (shoulder work) | 600 | m3/day | 750 | yd3/day
(per vehicle) |  | Medium (or truck work) | 1500 | m3/day | 2000 | yd3/day
|  | Large (or scraper work) | 3000 | m3/day | 4000 | yd3/day
| Excavation | Small (shoulder work) | 1000 | m3/day | 1300 | yd3/day
|  | Medium (or truck work) | 3000 | m3/day | 4000 | yd3/day
|  | Large (or scraper work) | 4500 | m3/day | 6000 | yd3/day
| Borrow | Truck | 3000 | m3/day | 4000 | yd3/day
|  | Scraper | 4500 | m3/day | 6000 | yd3/day
| Rock - Blasting | Small | 500 | m3/day | 650 | yd3/day
|  | Large | 1500 | m3/day | 2000 | yd3/day
| Muck Exc. |  | 500 | m3/day | 650 | yd3/day
| Street Exc. |  | 500 | m3/day | 650 | yd3/day
Aggregate | Base Course | Small (tonnage) | 1800 | tons/day | 2000 | tons/day
|  | Medium (volume) | 2000 | m3/day | 2600 | yd3/day
|  | Large | 3000 | m3/day | 4000 | yd3/day
| Pulverization |  | 15000 | m2/day | 18000 | yd2/day
| CTB |  | 1000 | m3/day | 1300 | yd3/day
Drainage | Culverts | ≤ 18" | 90 | m/day | 300 | ft/day
|  | = 24" | 60 | m/day | 200 | ft/day
|  | > 24" | 45 | m/day | 150 | ft/day
|  | RCB | 10 | m/day | 30 | ft/day
| Storm Drain | Pipe (avg. depth, 6-8 ft; conventional backfill) | 100 | m/day | 330 | ft/day
|  | Manholes/Inlets | 4 | each/day | 4 | each/day
Plant Mix | Cold Milling | Mainline | 30000 | m2/day | 35000 | yd2/day
|  | Taper | 250 | m2/day | 300 | yd2/day
| Cold Recycle |  | 3 | lane km/day | 2 | lane mi/day
| PMS |  | 3000 | tons/day | 3300 | tons/day
| PMS Urban |  | 2000 | tons/day | 2200 | tons/day
| Seal & Cover |  | 12 | lane km/day | 7.5 | lane mi/day
| Rumble Strips |  | 8 | lane km/day | 5 | lane mi/day
Concrete Paving | PCCP | Uniform Width | 8300 | m2/day | 10000 | yd2/day
|  | Non-uniform Width | 1600 | m2/day | 2000 | yd2/day
| Repair | Grinding | 3000 | m2/day | 3500 | yd2/day
|  | Joint Sealing | 3000 | m/day | 10000 | ft/day
Pavement Markings | Epoxy | Small | 2 | days | 2 | days
|  | Large | 4 | days | 4 | days
|  | Words & Symbols | additional 1-2 | days | additional 1-2 | days
| Thermoplastic | Intersection | 3 | days | 3 | days
Miscellaneous | Curb & Gutter |  | 300 | m/day | 1000 | ft/day
| Sidewalk |  | 250 | m2/day | 300 | yd2/day
| Fencing | Woven wire/Barbwire | 300 | m/day | 1000 | ft/day
|  | Chain Link | 200 | m/day | 600 | ft/day
| Guardrail | Concrete | 365 | m/day | 1200 | ft/day
|  | Steel | 225 | m/day | 750 | ft/day
| Vegetation | Seeding | 5 | ha/day | 12 | acre/day
|  | Sodding | 3000 | m2/day | 3500 | yd2/day