## Notes
Each row has a number associated with an activity in order for the filter to work. To reduce noise in the worksheet numbers below the first row are formatted with white text. To see effect, add a colored fill color to this column.
The worksheet has activities from both the Consultant Design Flowchart and the Consultant Wetland Mitigation Desgin Flowchart combined.
The subtotal function is used for subtotals as a more efficient function then the sum funtion. If there are other subtotals within ref1:ref2 (or nested subtotals), these nested subtotals are ignored to avoid double counting.
SUTOTAL(function_num, ref1:ref2) When funtion_num=9, the subtotal function sums all the rows including hidden rows. The subtotal function ignores any rows that are not included as the result of a filter, no matter which funtion_num value you use.
Survey Crew: Past estimate shells had a colum for survey/drill crew. The hours input represented a crew of two people with the following rate also representing two people. This did not align with the rest of the spread sheet or how Consultants calculated hours for survey. In addition this column applied to a limited number of activities. Therefore the column has been changed to "other" to allow more fexibility for its use. In addition, the hours input are for one person to be consistent with the rest of the spread sheet.

## Estimate
PROJECT: Rocker Interchange |  |  |  | Estimate Prepared By: BLM
UPN: 7777000 PE |  |  |  | DATE: | 2021-04-12
Activity | Tasks | Total Hours | Principal | Proj. Mgr. | Proj. Eng. | Design Eng. | CADD Tech. | Other | Clerc.
100 | INTERACTIVE PROJECT EVAL.
100 | Attend Scoping Meeting | 0
100 | Develop Project schedule | 0
100 | Determine project activities and cost proposal | 0
100 |  | 0
100 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | PUBLIC INVOLVEMENT
101 | Public and Stakeholder Involvement Plan | 0
101 | Draft and Transmit News Release | 0
101 | Prepare Project Website | 0
101 | Prepare/Conduct Informational Meeting | 0
101 |  | 0
101 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | Alternatives Analysis
102 | Compile available project data | 0
102 | Determine project alternatives | 0
102 | Screen Alternatives | 0
102 | Risk Analysis | 0
102 | QA/QC of Deliverables | 0
102 |  | 0
102 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | Preliminary Conceptual Mitigation Plans
103 | Field Review Meeting | 0
103 | Draft Conceptual Mitigation Report | 0
103 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | Access Control Goals and Objectives
104 | Prepare Goals & Objective Statement | 0
104 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 | Environmental Wetland Evaluation
105 | Cultural Resources Report | 0
105 | Hazardous Materials ISA Report | 0
105 | Biological Resource Report | 0
105 | Wetlands Finding Report | 0
105 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | PRELIMINARY GEOTECH & Surfacing
106 | Field Investigation of the existing Surfacing Section | 0
106 | Investigate and Report on culvert conditions | 0
106 | Conduct Preliminary Subsurface Investigation | 0
106 | Preliminary Geotechnical Review | 0
106 | Prepare Preliminary Surfacing Typical Sections | 0
106 | QA/QC of Deliverables | 0
106 |  | 0
106 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 | Geotechnical Wetland Evaluation
107 | Geotechnical Investigation | 0
107 | Geotechnical Report | 0
107 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 | CONTROL SURVEY
108 | Vertical Control Survey | 0
108 | Horizontal Control Survey | 0
108 | Computation and Adjustment Sheets | 0
108 | Recovery Descriptions | 0
108 | Coordinate Listings | 0
108 | Control Diagram | 0
108 | Calibration Baseline Reports | 0
108 | Peg Test Notes | 0
108 | Survey Piezometer Locations | 0
108 | QA/QC of Deliverables | 0
108 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
109 | Wildlife Accomodation Recommendation Memo
109 | Summarize wildlife needs | 0
109 | Resource Coordination | 0
109 | Accomodation Recommendations | 0
109 |  | 0
109 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | PRELIMINARY RIGHT OF WAY
110 | Ownership Report | 0
110 | Relocation Assistance Conceptual Study | 0
110 | Access Control Study & Recommendations | 0
110 | Irrigation Report | 0
110 | Cadastral Survey Request | 0
110 |  | 0
110 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | ENVIRONMENTAL ENGINEERING ANALYSES REPORT
111 | Draft Engineering Analyses Report | 0
111 | Final Engineering Analyses Report | 0
111 |  | 0
111 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
112 | PRELIMINARY TRAFFIC REPORT
112 | Data Collection and Review | 0
112 | Traffic/Safety Review and Analysis | 0
112 | Preliminary Traffic Reports | 0
112 | Prepare Preliminary Geometrics Report | 0
112 | QA/QC of Deliverables | 0
112 |  | 0
112 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
113 | PRELIMINARY UTILITY CONFLICTS/S.U.E.
113 | Coordination with Utility Companies & Kickoff Meeting | 0
113 | Subsurface Utility Engineering (Phase I) | 0
113 | Utility Coordination Meeting Minutes | 0
113 | QA/QC of Deliverables | 0
113 |  | 0
113 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
114 | PRELIMINARY BRIDGE LAYOUT
114 | Size, Type, Location Study & Report w/Cost Estimate | 0
114 | Preliminary Bridge Layout Plans | 0
114 | Order Bridge Cores | 0
114 | Preliminary Foundation Design | 0
114 |  | 0
114 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
116 | PRELIMINARY ENVIRONMENTAL DOCUMENT OR CATEGORICAL EXCLUSION/SECTION 4(f) EVALUATION
116 | Preliminary Site Investigation Report (if applicable) | 0
116 | Develop Preliminary Environmental Document or Preliminary Categorical Exclusion | 0
116 | Section 4(f) Evaluation | 0
116 |  | 0
116 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 | Draft Purpose and Need
117 | Draft Purpose and Need Statement | 0
117 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
118 | ROADWAY ALIGNMENT PLAN
118 | Preliminary Alignment & Grade | 0
118 | Establish Major Control | 0
118 | Preliminary Plans Preparation | 0
118 | Preliminary Specifications/Cost Estimate | 0
118 | Work Zone Safety & Mobility | 0
118 | QA/QC of Deliverables | 0
118 |  | 0
118 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
119 | Conceptual Mitigation Design
119 | Preparation of conceptual design alternatives | 0
119 | Conceptual Mitigation Design Alternative Report | 0
119 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | CADASTRAL SURVEY
120 | Cadastral Survey - RW retracement | 0
120 | Cadastral Survey - Section Corner | 0
120 |  | 0
120 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
121 | ENGINEERING SURVEY
121 | Topographical Survey | 0
121 | Hydraulic Survey | 0
121 | Pick-Up Surveys | 0
121 | Develop Survey Strip Map | 0
121 |  | 0
121 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
122 | ALIGNMENT AND GRADE TRAFFIC
122 | Preliminary Geometric Details | 0
122 | Signing Study (Inventory) | 0
122 | QA/QC of Deliverables | 0
122 |  | 0
122 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
124 | FINALIZE ALIGNMENT AND GRADE
124 | Finalize Alignment and Grade | 0
124 | Alignment and Grade Review/Report | 0
124 | Comment Response Document | 0
124 |  | 0
124 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
125 | Finalize Conceptual Mitigation Design Selection
125 | Finalize preferred alternatives with MDT | 0
125 | Final Conceptual Design Report | 0
125 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127 | Place Existing R/W and Section Lines
127 | Finalize Existing R/W and Cadastral Survey(s) | 0
127 | Prepare R/W Files | 0
127 | Copies of GLO Plats, Corner Recordations, etc | 0
127 |  | 0
127 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
128 | PREPARE SCOPE OF WORK
128 | Prepare/Submit Scope of Work Report | 0
128 | Prepare Cost Estimate | 0
128 | Prepare Design Exception Request | 0
128 | Complete Willdlife Accomodations Decision Report | 0
128 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
170 | PRELIMINARY HYDRAULICS
170 | Kick-Off Meeting | 0
170 | Review FEMA Mapping & Historical Aerials | 0
170 | Prepare Location Hydraulic Study Report | 0
170 | Preliminary Hydraulic Design | 0
170 | Preliminary Hydraulics Report | 0
170 | Size Bridge Openings | 0
170 | QA/QC of Deliverables | 0
170 |  | 0
170 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
171 | Preliminary Hydraulics Report
171 | Evaluate Hydrology | 0
171 | Develop Preliminary Water Budget | 0
171 | Evaluation of landowner water rights | 0
171 | Prepare Preliminary Hydraulics Report | 0
171 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
177 | Cultural Resource Report
177 | Draft Cultural Resource Report | 0
177 | Final Cultural Resource Report | 0
177 |  | 0
177 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
178 | Request Environmental Information
178 | Draft request for Information Letters | 0
178 | Final request for Information Incorporating MDT comments | 0
178 |  | 0
178 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
179 | Preliminary Traffic Noise Study
179 | Preliminary Traffic Noise Analysis Report or ISA Form | 0
179 |  | 0
179 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
180 | Air Quality Conformity Determination
180 | Draft ISA Form Regarding Conformity of Project | 0
180 | Conformity Determination Letter (if required) | 0
180 | Final ISA Form or Memo Regarding Comformity of Project as necessary | 0
180 |  | 0
180 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
181 | Hazardous Materials/Substances and Water Quality ISA
181 | Draft ISA checklist or report | 0
181 | Final ISA checklist or report | 0
181 |  | 0
181 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
183 | Site Investigation for Hazardous Materials
183 | Land use Research | 0
183 | Subsurface Investigation | 0
183 | Coordination | 0
183 | Report | 0
183 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
182 | Biological Resource Report/Biological Assessment
182 | Draft Biological Resource Report | 0
182 | Final Biological Resource Report | 0
182 | Preliminary Biological Assessment | 0
182 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
185 | DETAILED NOISE STUDY
185 | Detailed Noise Analysis Report | 0
185 | Neighborhood opinion survey | 0
185 |  | 0
185 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SURVEY PHASE | TOTAL SURVEY PHASE HOURS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
115 | UTILITY CONFLICTS FOR PLAN IN HAND
115 | Subsurface Utility Engineering | 0
115 | Utility Conflict Report | 0
115 | QA/QC of Deliverables | 0
115 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
130 | FINAL GEOTECHNICAL & MATERIALS REPORT
130 | Complete pickup survey for soil borings and test pit | 0
130 | Process survey and update mapping | 0
130 | Log soil borings on plan and profile sheets | 0
130 | Coordinate with SK during drilling | 0
130 | Review and comment on draft and final reports. | 0
130 | Work plan development | 0
130 | Final report submittal, editing respond to questions. | 0
130 |  | 0
130 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
131 | DESIGN PUBLIC INVOLVEMENT
131 | Update Project Website | 0
131 | Draft and Transmit News Release | 0
131 | Prepare/Conduct Informational Meeting | 0
131 |  | 0
131 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
134 | PREPARE PLANS FOR PIH
134 | Prepare Road Plans-plan set, spec. provision, cost est | 0
134 | Workzone Safety & Mobility Plan | 0
134 | QA/QC of Deliverables | 0
134 |  | 0
134 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
135 | Prepare Mitigation Design
135 | Prepare Mitigation Plans, Specications & Cost Est. | 0
135 | QA/QC of Deliverables | 0
135 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
136 | PRELIMINARY STRUCTURE PLANS FOR PIH
136 | Prepare Structure Plans (bridge, walls,etc.) for PIH | 0
136 | Preliminary Structure Cost Estimate | 0
136 | QA/QC of Deliverables | 0
136 |  | 0
136 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
137 | Access Control Guidelines\Plan
137 | Prepare Access Management Guidelines | 0
137 | Prepare Access Contol Plans | 0
137 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
138 | PRELIMINARY R/W PLAN FOR PIH
138 | Preliminary R/W Plan Sheets and CADD Files | 0
138 | QA/QC of Deliverables | 0
138 |  | 0
138 |  | 0
138 |  | 0
138 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
140 | PLAN-IN-HAND
140 | Office Review | 0
140 | Field Review | 0
140 | Prepare Plan-In-Hand Report | 0
140 | Prepare Design Exceptions | 0
140 | Workzone Safety & Mobility Plan | 0
140 | Comment Response Document | 0
140 | QA/QC of Deliverables | 0
140 |  | 0
140 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
141 | Mitigation Design Plan In Hand
141 | Office Review | 0
141 | Field Review | 0
141 | Prepare Plan-In-Hand Report | 0
141 | Prepare Design Exceptions | 0
141 |  | 0
141 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
149 | Final Wetland Mitigation Permits
149 | Environmental Water Quality Permits | 0
149 | Compliance with Stream Protection Act | 0
149 | Cultural Mitigation | 0
149 | Storm Water Permits | 0
149 | Final Environmental Review | 0
149 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
153 | Final Mitigation Design Plan
153 | Revise Plans after PIH | 0
153 | QA/QC of Deliverables | 0
153 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
164 | PREPARE TRAFFIC PLANS FOR PIH
164 | Prepare Electrical Plans | 0
164 | Prepare Geometric details(Intersection, Roundabout interchange details, etc) | 0
164 | Prepare Signing and Striping Plans | 0
164 | Analyze traffic plans, special provisions, cost est. | 0
164 | QA/QC of Deliverables | 0
164 |  | 0
164 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
172 | FINAL HYDRAULICS REPORT
172 | Storm Drain Design | 0
172 | Size Box or Pipe Culverts | 0
172 | Size Irrigation Structures | 0
172 |  | 0
172 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
173 | Final Wetlands Hydraulics Report
173 | Final Hydraulics Report | 0
173 | Draft Water Rights application | 0
173 | Draft Flood Plain Permit Application | 0
173 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
184 | Biological Assessment
184 | Draft Biological Assessment | 0
184 | Final Biological Assessment | 0
184 |  | 0
184 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DESIGN PHASE | TOTAL DESIGN PHASE HOURS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
142 | R/W PLANS
142 | Determine Final Construction Limits | 0
142 | Complete Final R/W Plans | 0
142 | Review Cost Estimates for R/W | 0
142 | Prepare Route Descriptions | 0
142 |  | 0
142 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | R/W PLAN REVISIONS
144 | Revise R/W Plan Sheets and CADD Files | 0
144 | Prepare Exhibits | 0
144 |  | 0
144 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
146 | STRUCTURE DESIGN
146 | Complete Structure Plans | 0
146 | Structures Cost Estimate | 0
146 | Special Provisions | 0
146 | QA/QC of Deliverables | 0
146 |  | 0
146 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
147 | FINAL BRIDGE PLANS
147 | Final Bridge Plans | 0
147 | Special Provisions | 0
147 | Bridge Cost Estimate | 0
147 | QA/QC of Deliverables | 0
147 |  | 0
147 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
148 | FINAL ENVIRONMENTAL MATTERS & DRAFT PERMITS
148 | Environmental Water Quality Permits | 0
148 | Wetlands Finding Report | 0
148 | Cultural Mitigation | 0
148 | Final Environmental/Biological Review | 0
148 |  | 0
148 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
150 | R/W APPRAISALS
150 | Appraise R/W | 0
150 | Prepare Deeds | 0
150 |  | 0
150 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
152 | FINAL PLAN PREPARATION
152 | Revise Plans after PIH | 0
152 | QA/QC of Deliverables | 0
152 |  | 0
152 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
156 | R/W PLAN REVISIONS AFTER AUTHORIZATION (BLUE SHEETS)
156 | Revise R/W Plan & Deed Exhibits | 0
156 | Design Exception request (when applicable) | 0
156 |  | 0
156 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
158 | GEOTECHNICAL AND MATERIALS REVISIONS
158 | Finalize geotechnical design after PIH | 0
158 |  | 0
158 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
160 | PROCESS FOR CONDEMNATION
160 | Process For Condemnation | 0
160 |  | 0
160 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
162 | FINAL PLAN REVISIONS
162 | Revise Plans after Final Plans Review | 0
162 | Update Cost Estimate/Special Provisions | 0
162 | Comment Response Document | 0
162 | Finalize Traffic Management Plan | 0
162 | QA/QC of Deliverables | 0
162 |  | 0
162 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
163 | ADDITIONAL PLAN REVISIONS
163 | Address Questions from Blue Sheet Review | 0
163 | Revise Plans after Blue Sheet Review | 0
163 | Address Questions during Advertising | 0
163 | Check R/W agreements against PS&E | 0
163 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
165 | PREPARE TRAFFIC PLANS FOR FPR
165 | Prepare Electrical Plans | 0
165 | Prepare Geometric Details | 0
165 | Prepare Signing and Striping Plans | 0
165 | QA/QC of Deliverables | 0
165 |  | 0
165 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
166 | UTILITY PLANS
166 | Prepare/Complete/Submit Utility Plans | 0
166 | Complete Compliance Review Checklist | 0
166 |  | 0
166 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
167 | FINAL TRAFFIC DESIGN
167 | Finalize Electrical Plans | 0
167 | Finalize Geometric Details | 0
167 | Finalize Signing and Striping Plans | 0
167 | Finalize Special Provisions and Cost Estimate | 0
167 |  | 0
167 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
168 | ROW PUBLIC INVOLVEMENT
168 | Update Project Website | 0
168 | Draft and Transmit News Release | 0
168 | Prepare/Conduct Informational Meeting | 0
168 |  | 0
168 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
174 | FINAL HYDRAULIC UPDATES, PERMITS and REVISIONS
174 | Final Hydraulics Recommendations (R/W Related) | 0
174 | Prepare, Submit & Coordinate Regulatory Permits | 0
174 | Revise & Update Hydraulic Recommendations | 0
174 | Final Hydraulic Plans Updates | 0
174 |  | 0
174 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
175 | FINAL PLAN REVIEW
175 | Final Plan Office/Field Review | 0
175 | Submit Final Plan Review Report | 0
175 |  | 0
175 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
190 | Utility Plan Revisions
190 | Revise Utility plans to reflect all R/W changes. | 0
190 |  | 0
190 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R/W PHASE | TOTAL RIGHT OF WAY PHASE HOURS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Project Hours | Total Project Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on A5: Author: Each row needs to have a number in it in order for the filter to work. To reduce noise in the worksheet activity numbers below the first row are formatted in white text.
Note on A358: Author: Activity 150 is included in the RW phase. Do not include in the PE proposal.
Note on A368: Author: Activity 156 is included in the RW phase. Do not include in the PE proposal.
Note on A377: Author: Activity 160 is included in the RW phase. Do not include in PE proposal.

## Summary
PROJECT: Rocker Interchange |  |  | Estimate Prepared By: BLM
UPN: 7777000 PE |  |  | DATE: | 2021-04-12 | 0 | 0 | 0 | 0
COST SUMMARY
|  | Hours | % of total | Rate |  |  |  | Extension
| Principal | 0 | #DIV/0! |  |  |  |  | 0
| Project Manager | 0 | #DIV/0! |  |  |  |  | 0
| Project Engineer | 0 | #DIV/0! |  |  |  |  | 0
| Design Engineer | 0 | #DIV/0! |  |  |  |  | 0
| CADD/Designer | 0 | #DIV/0! |  |  |  |  | 0
| Other | 0 | #DIV/0! |  |  |  |  | 0
| Clerical | 0 | #DIV/0! |  |  |  |  | 0
| TOTAL HOURS | 0
|  |  |  | LABOR SUBTOTAL |  |  |  | 0
GENERAL OVERHEAD @ |  |  |  | OVERHEAD SUBTOTAL |  |  |  | 0
|  |  | TOTAL LABOR/OVERHEAD |  |  |  |  | 0
DIRECT NONLABOR
| Miscellaneous (Blueline prints, mylars, multilith paper, telephone, postage, misc. equipment rental, maps, photos, survey mtls., display boards, etc.) | [6 empty] | 0
| Computer | Hours | 0 | Per Hour | 10 |  |  | 0
| Title commitments | Parcels |  | Per Parcel | 400 |  |  | 0
| Vehicle Rental | Days |  | Per Month | 271 | GSA |  | 0
| Mileage | Miles |  | Per Mile | 0.67 | GSA |  | 0
| Airline Trips | Trips |  | Per Trip | 600 |  |  | 0
| Lodging | Days |  | Per Day | 117 | GSA |  | 0
| Meals | Days |  | Per Day | 59 | GSA |  | 0
Other
[5 empty] | TOTAL DIRECT NONLABOR |  |  | 0
OUTSIDE SERVICES AND SUBCONTRACTS
Drilling Contractor
Soils/Geotechnical Survey/Report/Testing
Cultural Resource Studies/Report
Noise Study
Traffic Study/Report
Biological Resources Studies/Report
Surveys
Subsurface Utility Engineering
Hazardous Materials (Initial Site Assessment)
Landscaping Plans
Electrical/Lighting Signalization etc
Aerial Photography/Mapping
Other
|  | TOTAL OUTSIDE SERVICES AND SUBCONTRACTS | [5 empty] | 0
RECAPITULATION
| Total Labor/ Overhead | [6 empty] | 0
| Total Direct NonLabor | [6 empty] | 0
| Total Outside Services & Subcontracts | [6 empty] | 0
| Profit (12% of Total Labor Costs) | [6 empty] | 0
|  |  |  | TOTAL ESTIMATED COST |  |  |  | 0
Note on G31: Author: GSA does not have a daily vehicle rental rate. They use the monthly rate divided by 30.
Note on G34: Author: GSA rate + tax