## Sample-Instructions
MDT PROGRESS REPORT (Construction Engineering Services)
Project Name: |  | Montana Highway
Project Number: |  | NH 9-3(45)7
Project UPN: |  | 9876000
Consultant: |  | ABC, Inc.
Period: |  | June 1, 2020 – June 30, 2020
Approved by: |  | Tom, ABC Project manager
General CE Services and Specific CE Tasks
Date of Request | Request # | Request made by | Description of the Request | Who responded to Request | Time spent on Request (total hrs) | Response/ Completion Date
2020-05-21 | G1 | David Hill | Review storm drainage issue on 1st Ave. | Jack Smith & Chris Johnson | 12 | 2020-05-30 | General request number use a G designation, G1
2020-05-25 | G2 | Robert Street | Utility was hit when driving pile; Responded to the issue and checked additional locations do not have conflicts; Potential E&O as identified by MDT* | Joe Brown | 8* (not invoiced) | 2020-05-30
2020-06-11 | S1 | David Hill | Review of bridge girder fabrication | Mike Steel | 24 | 2020-06-25 | Specific request number use an S designation, S1
2020-07-15 | S2 | R. Street | Review of retaining wall design | Bill Beam | 8
*Note: Potential E&O tasks cannot be invoiced until the E&O issue is resolved and determined whether it is eligible for payment.
Shade tasks that have been completed in previous time periods.
Budget Expended for General and Specific CE Tasks
Task Number | % Budget Expended | Task Description
General | 55% | General Budget to Answer Questions and Clarifications
1 | 95% | Review of Bridge Contract submittals
2 | 50% | Geotechnical support for bridge foundation construction
3 | 75% | Review of Retaining wall submittals
*Note: Make sure row heights are adjusted on merged cells so your content is fully shown.
Project critical issues/Potential risks
Task Number | Request # | Description of the potential issue or risk
1 | n/a | Bridge submittals are 95% expended, due to additional reviews for design changes, may need to increase the budget for additional reviews.
General | G2 | Potential E&O issue, E&O process will need to be completed by MDT
*Note: Make sure row heights are adjusted on merged cells so your content is fully shown.

## Blank-Template
MDT PROGRESS REPORT (Construction Engineering Services)
Project Name:
Project Number:
Project UPN:
Consultant:
Period:
Approved by:
General CE Services and Specific CE Tasks
Date of Request | Request # | Request made by | Description of the Request | Who responded to Request | Time spent on Request (total hrs) | Response/ Completion Date
*Note: Potential E&O tasks cannot be invoiced until the E&O issue is resolved and determined whether it is eligible for payment.
Shade tasks that have been completed in previous time periods.
Budget Expended for General and Specific CE Tasks
Task Number | % Budget Expended | Task Description
General |  | General Budget to Answer Questions and Clarifications
1
2
3
*Note: Make sure row heights are adjusted on merged cells so your content is fully shown.
Project critical issues/Potential risks
Task Number | Request # | Description of the potential issue or risk
*Note: Make sure row heights are adjusted on merged cells so your content is fully shown.