1. CPM Schedule UpDATES [108] (added 8-8-24)

Rescind the first paragraph of Subsection 108.03.2 B. 4 which states “Each month of the project, one week before the end of the project’s monthly estimate cycle, submit an electronic .xer file using Primavera P6 and a .pdf file containing:” and replace with the following:

“Notify the Project Manager in writing by the Notice to Proceed date or at the pre-construction conference, whichever is sooner, of the day the schedule update will be submitted each month. Once the date is selected, it will not be changed. If a date is not selected, submit the schedule no later than 7 calendar before the end of the project’s monthly estimate cycle.

Each month of the project submit an electronic .xer file using Primavera P6 and a .PDF file containing: “